## Agile Project Backlog
Agile Product Backlog
PROJECT DESCRIPTION
Learner's Academy, needs an online management system for back-office application with single administrator login. The system should keeps track of it's classes, subjects, students, and teachers in the school.
PROJECT BACKLOG
ID | As a | I want to | So that | Priority | Story point | Sprint Assignment | Status
[8 empty] | Comments relating to a story point changing, a new story added, or a story removed. | Initial numeric estimate (size) concluded during Sprint Review, Hours | Hours | Hours | Hours | Hours | Hours
1 | Admin | Have a home page | Application should have a landing page | Must | 25 |  | Done
2 | Admin | Have a option to admin login | To ensure that the Flight Booking authentication ahead | Must | 29 |  | Done
3 | Admin | Create the databases table | To ensure the Data is stored in the admin page module | Must | 35 |  | Done
4 | Admin | Welcome Page | To Move ahead to view the flights | Must | 35 |  | Done
5 | Admin | Flight Schedule | Look at the Flights you want to choose | Must | 35 |  | Done
6 | Admin | Flight Availability | Lock and Book the Flights | Must | 30 |  | Done
7 | Admin | Flight Ticket Booking | Flight List and Book List Details | Must | 30 |  | Done
8 | Admin | Confirm | Confirmation and Logout Page | Must | 28 |  | Done
9 | User | Have a option to logout and view my flights | I can book my flights and logout | Optional | 18 |  | Incomplete
10 | Admin | Have a error page | All the errors will be handled | Optional | 25 |  | Incomplete - User Part

## Agile Sprint Backlog
Agile Sprint Backlog
SUMMARY
CHANGE IN SCOPE
| Original Story Points |  | 290
| New Points |  | .
| Total Points |  | 274
| CHANGE IN SCOPE |  | -5.839%
SPRINT BACKLOG
ID | Backlog task | Assigned to | Story points | New points? | Release | Status | Business value | Change management notes | Initial estimate
[8 empty] | Comments relating to a story point changing, a new story added, or a story removed. | Initial numeric estimate (size) concluded during Sprint Review, Hours
1 | Have a home page
1.2 | Design the UI | Harshad Kalantri | 5 | FALSE | 1 | Done | High |  | 5
1.3 | Design the Backend | Harshad Kalantri | 5 | FALSE | 1 | Done | High |  | 5
1.4 | Code the UI | Harshad Kalantri | 5 | FALSE | 1 | Done | High |  | 5
1.5 | Code the Backend | Harshad Kalantri | 5 | FALSE | 1 | Done | High |  | 5
1.6 | Push the code to GitHub | Harshad Kalantri | 5 | FALSE | 1 | Done | Low |  | 5
2 | To ensure that the Flight Booking authentication ahead
2.1 | Design the Database | Harshad Kalantri | 5 | FALSE | 1 | Done | High |  | 5
2.2 | Design the UI | Harshad Kalantri | 4 | FALSE | 1 | Done | High |  | 4
2.3 | Design the Backend | Harshad Kalantri | 5 | FALSE | 1 | Done | High |  | 5
2.4 | Code the Database | Harshad Kalantri | 5 | FALSE | 1 | Done | High |  | 5
2.5 | Code the UI | Harshad Kalantri | 5 | FALSE | 1 | Done | High |  | 5
2.6 | Code the Backend | Harshad Kalantri | 5 | FALSE | 1 | Done | High |  | 5
2.7 | Test the functionality | Harshad Kalantri | 0 | FALSE | 1 | Done | Medium |  | 0
2.8 | Push the code to GitHub | Harshad Kalantri | 0 | FALSE | 1 | Done | Low |  | 0
3 | To ensure the Data is stored in the admin page module
3.1 | Design the Database | Harshad Kalantri | 5 | FALSE | 1 | Done | High |  | 5
3.2 | Design the UI | Harshad Kalantri | 5 | FALSE | 1 | Done | High |  | 5
3.3 | Design the Backend | Harshad Kalantri | 5 | FALSE | 1 | Done | High |  | 5
3.4 | Code the Database | Harshad Kalantri | 5 | FALSE | 1 | Done | High |  | 5
3.5 | Code the UI | Harshad Kalantri | 5 | FALSE | 1 | Done | High |  | 5
3.6 | Code the Backend | Harshad Kalantri | 5 | FALSE | 1 | Done | High |  | 5
3.7 | Test the functionality | Harshad Kalantri | 5 | FALSE | 1 | Done | Medium |  | 5
3.8 | Push the code to GitHub | Harshad Kalantri | 0 | FALSE | 1 | Done | Low |  | 0
4 | To Move ahead to view the flights
4.1 | Design the Database | Harshad Kalantri | 5 | FALSE | 1 | Done | High |  | 5
4.2 | Design the UI | Harshad Kalantri | 5 | FALSE | 1 | Done | High |  | 5
4.3 | Design the Backend | Harshad Kalantri | 5 | FALSE | 1 | Done | High |  | 5
4.4 | Code the Database | Harshad Kalantri | 5 | FALSE | 1 | Done | High |  | 5
4.5 | Code the UI | Harshad Kalantri | 5 | FALSE | 1 | Done | High |  | 5
4.6 | Code the Backend | Harshad Kalantri | 5 | FALSE | 1 | Done | High |  | 5
4.7 | Test the functionality | Harshad Kalantri | 5 | FALSE | 1 | Done | Medium |  | 5
4.8 | Push the code to GitHub | Harshad Kalantri | 0 | FALSE | 1 | Done | Low |  | 0
5 | Look at the Flights you want to choose
5.1 | Design the Database | Harshad Kalantri | 5 | FALSE | 1 | Done | High |  | 5
5.2 | Design the UI | Harshad Kalantri | 5 | FALSE | 1 | Done | High |  | 5
5.3 | Design the Backend | Harshad Kalantri | 5 | FALSE | 1 | Done | High |  | 5
5.4 | Code the Database | Harshad Kalantri | 5 | FALSE | 1 | Done | High |  | 5
5.5 | Code the UI | Harshad Kalantri | 5 | FALSE | 1 | Done | High |  | 5
5.6 | Code the Backend | Harshad Kalantri | 5 | FALSE | 1 | Done | High |  | 5
5.7 | Test the functionality | Harshad Kalantri | 5 | FALSE | 1 | Done | Medium |  | 5
5.8 | Push the code to GitHub | Harshad Kalantri | 0 | FALSE | 1 | Done | Low |  | 0
6 | Lock and Book the Flights
6.1 | Design the Database | Harshad Kalantri | 5 | FALSE | 1 | Done | High |  | 5
6.2 | Design the UI | Harshad Kalantri | 2 | FALSE | 1 | Done | High |  | 2
6.3 | Design the Backend | Harshad Kalantri | 5 | FALSE | 1 | Done | High |  | 5
6.4 | Code the Database | Harshad Kalantri | 5 | FALSE | 1 | Done | High |  | 5
6.5 | Code the UI | Harshad Kalantri | 5 | FALSE | 1 | Done | High |  | 5
6.6 | Code the Backend | Harshad Kalantri | 5 | FALSE | 1 | Done | High |  | 5
6.7 | Test the functionality | Harshad Kalantri | 3 | FALSE | 1 | Done | Medium |  | 3
6.8 | Push the code to GitHub | Harshad Kalantri | 0 | FALSE | 1 | Done | Low |  | 0
7 | Flight List and Book List Details
7.1 | Design the Database | Harshad Kalantri | 5 | FALSE | 1 | Done | High |  | 5
7.2 | Design the UI | Harshad Kalantri | 2 | FALSE | 1 | Done | High |  | 2
7.3 | Design the Backend | Harshad Kalantri | 5 | FALSE | 1 | Done | High |  | 5
7.4 | Code the Database | Harshad Kalantri | 5 | FALSE | 1 | Done | High |  | 5
7.5 | Code the UI | Harshad Kalantri | 5 | FALSE | 1 | Done | High |  | 5
7.6 | Code the Backend | Harshad Kalantri | 5 | FALSE | 1 | Done | High |  | 5
7.7 | Test the functionality | Harshad Kalantri | 3 | FALSE | 1 | Done | Medium |  | 3
7.8 | Push the code to GitHub | Harshad Kalantri | 0 | FALSE | 1 | Done | Low |  | 0
8 | Confirmation and Logout Page
8.1 | Design the Database | Harshad Kalantri | 5 | FALSE | 1 | Done | High |  | 5
8.2 | Design the UI | Harshad Kalantri | 5 | FALSE | 1 | Done | High |  | 5
8.3 | Design the Backend | Harshad Kalantri | 5 | FALSE | 1 | Done | High |  | 5
8.4 | Code the Database | Harshad Kalantri | 5 | FALSE | 1 | Done | High |  | 5
8.5 | Code the UI | Harshad Kalantri | 0 | FALSE | 1 | Done | High |  | 0
8.6 | Code the Backend | Harshad Kalantri | 5 | FALSE | 1 | Done | High |  | 5
8.7 | Test the functionality | Harshad Kalantri | 3 | FALSE | 1 | Done | Medium |  | 3
8.8 | Push the code to GitHub | Harshad Kalantri | 0 | FALSE | 1 | Done | Low |  | 0
9 | As a User, I can book my flights and logout+C100
9.1 | Design the UI | Harshad Kalantri | 3 | FALSE | 1 | Done | High |  | 3
9.2 | Design the Backend | Harshad Kalantri | 3 | FALSE | 1 | Cancelled | High |  | 3
9.3 | Code the UI | Harshad Kalantri | 3 | FALSE | 1 | Cancelled | High |  | 1
9.4 | Code the Backend | Harshad Kalantri | 3 | FALSE | 1 | Cancelled | High |  | 1
9.5 | Test the functionality | Harshad Kalantri | 3 | FALSE | 1 | Cancelled | Medium |  | 1
9.6 | Push the code to GitHub | Harshad Kalantri | 3 | FALSE | 1 | Cancelled | Low |  | 0
10 | As a Admin, I should have a error page. So, that all the errors will be handled.
10.1 | Design the UI | Harshad Kalantri | 5 | FALSE | 1 | Done | High |  | 5
10.2 | Design the Backend | Harshad Kalantri | 5 | FALSE | 1 | Done | High |  | 4
10.3 | Code the UI | Harshad Kalantri | 5 | FALSE | 1 | Done | High |  | 4
10.4 | Code the Backend | Harshad Kalantri | 5 | FALSE | 1 | Done | Low |  | 2
10.5 | Test the functionality | Harshad Kalantri | 5 | FALSE | 1 | Done | Medium |  | 3
10.6 | Push the code to GitHub | Harshad Kalantri | 0 | FALSE | 1 | Done | Low |  | 0